# DevHive

Project Description & 30-Day MVP Execution Plan

Engineering orchestration • branch-aware access • persistent engineering memory

# 1. Project Overview

DevHive is an orchestration platform for engineering teams that combines Git-based project workflow, branch-aware role permissions, and a persistent RAG-powered engineering memory. Its purpose is to preserve not only what changed in a codebase, but also who changed it, when it changed, why it changed, and the engineering context surrounding the change.

# 2. Core Problem

Git preserves code history well, but the reasoning behind many changes is quickly lost.

Engineering teams often manage permissions at a coarse repository or project level instead of tying access to development workflow.

Important implementation decisions remain scattered across commits, chat, issues, documents, and individual memory.

When engineers leave a project, much of the reasoning and context behind the code disappears.

# 3. DevHive Solution

DevHive adds an orchestration and memory layer around Git. Each project has a role hierarchy, and roles determine which branches and operations a developer can access. Before a push, a lightweight TUI captures TCC — Thought, Code, Comment — and associates it with the resulting Git commit. Every accepted push becomes a structured engineering-memory document that is indexed for retrieval.

# 4. Core Workflow

| Step | Component | Action |
| --- | --- | --- |
| 1 | Developer | Works inside a DevHive-managed project and branch. |
| 2 | Permission Engine | Validates the user's role against the target branch and requested operation. |
| 3 | Code Change | Developer modifies the local repository normally. |
| 4 | TCC Gate | TUI collects Thought, Code/Change summary, and Comment before push. |
| 5 | Git Commit / Push | DevHive records the commit, diff metadata, branch, author, and TCC. |
| 6 | Memory Ingestion | The change is transformed into structured RAG documents/chunks. |
| 7 | Engineering Search | Authorized users can retrieve historical decisions and code context. |

# 5. MVP Scope

Multi-project workspace model.

Users, roles, and project membership.

Branch-to-role permission mapping.

Protected branch operations for push/merge access.

GitHub repository integration for the MVP.

CLI/TUI client for authentication, project/branch context, TCC capture, and push.

Commit metadata + diff metadata ingestion.

RAG indexing of TCC, commit metadata, changed files, and selected code context.

Semantic search over engineering history.

Permission-aware retrieval so users cannot query memory they are not authorized to access.

Minimal web dashboard for projects, members, branches, commits, and searchable memory.

Audit log for authorization decisions and ingestion events.

# 6. Explicitly Out of Scope for Month 1

GitLab/Bitbucket integrations.

Real-time collaborative code editing.

AI code generation/autonomous coding agents.

Complex enterprise SSO/SAML.

Fully custom Git hosting.

Distributed multi-region deployment.

Advanced analytics and productivity scoring.

Automatic semantic understanding of every line of every repository.

# 7. Recommended Tech Stack

| Layer | Technology | Reason |
| --- | --- | --- |
| Backend API | Python + FastAPI | Fast development, strong typing ecosystem, async support, easy AI/RAG integration. |
| Authorization | PostgreSQL + application RBAC/branch policy engine | Explicit, testable permission model with relational consistency. |
| Database | PostgreSQL + SQLAlchemy + Alembic | Users, projects, roles, branches, commits, audit records and metadata. |
| Vector Search | Qdrant | Purpose-built vector database with filtering suitable for project/role-aware retrieval. |
| Embeddings | BGE-M3 via local inference | Strong multilingual/general retrieval with a local/self-hostable path. |
| RAG | LlamaIndex | Fast MVP implementation for ingestion, chunking and retrieval while keeping the storage layer explicit. |
| LLM | OpenRouter-compatible provider abstraction | Keeps model choice flexible during development. |
| Git Integration | Git CLI + GitHub REST API | Git remains the source of truth; GitHub handles remote repository integration. |
| TUI | Python + Textual | Rich terminal interface with a practical path to cross-platform packaging. |
| Web Frontend | Next.js + TypeScript + Tailwind CSS | Fast dashboard development and a clean TypeScript UI. |
| Auth | GitHub OAuth + short-lived application sessions | Simple MVP identity flow without building a full identity provider. |
| Background Jobs | Redis + ARQ | Simple async ingestion queue without adding a heavy workflow platform. |
| Deployment | Docker Compose locally; Render/Railway + managed PostgreSQL/Qdrant for MVP | Low operational overhead during a one-month build. |
| Testing | Pytest + HTTPX + Playwright | Backend, API and end-to-end coverage. |

# 8. Architecture

The MVP should use a modular monolith rather than microservices. This keeps the one-month target realistic while preserving clear boundaries that can later be extracted into services.

Next.js Dashboard → FastAPI API → PostgreSQL

CLI/TUI → FastAPI API + local Git repository

FastAPI → Authorization Policy Engine → project/branch/role rules

Push event / TCC submission → Redis queue → ingestion worker

Ingestion worker → PostgreSQL metadata + Qdrant vectors

RAG query → permission filter → Qdrant retrieval → context assembly → LLM answer

GitHub remains the remote Git source of truth; DevHive stores metadata and engineering memory.

# 9. Permission Model

Use explicit numeric levels initially; avoid an overly complicated Discord-like hierarchy in the MVP.

| Level | Example Role | Typical Access |
| --- | --- | --- |
| Level 1 | Observer | Read project metadata and permitted memory. |
| Level 2 | Contributor | Work on feature branches and submit TCC/pushes. |
| Level 3 | Developer | Additional development branches and broader project access. |
| Level 4 | Maintainer | Protected branch operations and merge authority. |
| Level 5 | Owner | Project configuration, roles, branch policies, and audit access. |

Important: role level alone is not sufficient. Each project defines which levels may operate on each branch. For example, feature/* may accept Level 2+, development may require Level 3+, and main may require Level 4+.

# 10. RAG Document Model

Each push should create a durable engineering-memory record containing:

Project ID and repository ID.

Branch and commit SHA.

Author/user ID and timestamp.

Parent commit SHA.

Commit message.

Files changed and change statistics.

TCC: Thought, Code/Change summary, Comment.

Relevant diff hunks or normalized diff summary.

Access scope / minimum role required.

Ingestion version and embedding/model metadata.

The original Git repository remains authoritative for source code. DevHive's RAG is the searchable memory layer, not a replacement for Git.

# 11. 30-Day Timeline

| Days | Phase | Work | Deliverable |
| --- | --- | --- | --- |
| Days 1–2 | Foundation | Finalize data model, permission semantics, repository structure, Docker environment, CI, development conventions. | Architecture baseline running locally. |
| Days 3–5 | Auth + Projects | GitHub OAuth, users, projects, memberships, roles, sessions, project CRUD. | A user can create/access a project. |
| Days 6–8 | Branch Permissions | Branch policies, role levels, operation checks, authorization middleware, audit events. | Unauthorized branch operations are rejected. |
| Days 9–11 | Git Integration | Repository registration, Git metadata parser, commit/diff extraction, GitHub integration. | DevHive can understand repository/branch/commit state. |
| Days 12–14 | TCC TUI | Build Textual TUI, login/session, project/branch selection, TCC capture, local validation. | Developer can complete a TCC flow from terminal. |
| Days 15–17 | Push Gate | Integrate TCC with commit/push workflow, branch authorization, commit association, failure/retry handling. | Protected push workflow works end-to-end. |
| Days 18–20 | RAG Ingestion | Define document schema, chunking, embeddings, Qdrant collections, metadata filters, background worker. | Every accepted push can become searchable memory. |
| Days 21–23 | RAG Retrieval | Permission-aware retrieval, semantic search, context assembly, citations to commit/branch, basic LLM answer generation. | Users can ask why/how questions about project history. |
| Days 24–26 | Dashboard | Project overview, members/roles, branches, commits, TCC records, audit log, memory search UI. | Usable web control plane. |
| Days 27–28 | Security + Testing | Permission test matrix, retrieval isolation tests, injection validation, API tests, TUI tests, end-to-end flows. | MVP security and regression baseline. |
| Day 29 | Deployment | Production environment, managed DB/vector store, secrets, migrations, logging, monitoring, backup strategy. | Deployed staging/production MVP. |
| Day 30 | Demo + Hardening | Bug fixing, performance pass, documentation, sample repository, demo scenario, release checklist. | DevHive v0.1 MVP ready. |

# 12. Weekly Milestones

End of Week 1: Identity, projects, memberships, roles and branch policy engine work.

End of Week 2: Git integration and a working TCC-gated terminal workflow.

End of Week 3: Push-to-RAG ingestion and permission-aware retrieval work.

End of Week 4: Dashboard, security testing, deployment, documentation and demo.

# 13. Definition of Done

A new engineer can authenticate and join a project.

A project owner can define roles and branch access levels.

A lower-level user cannot push or perform protected operations on a higher-level branch.

A developer can make a local change and complete TCC in the TUI.

The resulting commit is linked to the TCC record.

The push creates an ingestion event and searchable RAG document.

A user can ask a historical engineering question and receive relevant commit/TCC context.

Retrieval respects project and role permissions.

An administrator can inspect project history and audit events.

The entire MVP can be demonstrated using one real GitHub repository.

# 14. Key Engineering Decisions

Git is the source of truth for code; DevHive is the orchestration and memory layer.

Start as a modular monolith. Do not spend the first month building microservices.

Use PostgreSQL for transactional state and Qdrant for vector retrieval.

Keep TCC mandatory only at the push boundary for protected/managed repositories in the MVP.

Store immutable ingestion records. Never overwrite historical reasoning.

Attach authorization scope to every RAG document so retrieval cannot bypass branch/project permissions.

Make ingestion asynchronous so a slow embedding/LLM provider never blocks the core Git workflow.

Use provider abstraction for embeddings/LLMs so the MVP is not locked to one model vendor.

# 15. Month-1 Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Scope explosion | Freeze MVP at GitHub + one Git workflow + one TUI + one dashboard. |
| Permission bugs | Write authorization tests before adding advanced UI features. |
| RAG quality | Prioritize structured metadata and commit/diff retrieval before fancy agentic RAG. |
| Push reliability | Use an explicit state machine: TCC captured → commit associated → push authorized → ingestion queued. |
| Provider outages | Abstract embeddings/LLM calls and make ingestion retryable. |
| Security leakage | Apply project/branch/role filters before vector retrieval, not after the LLM response. |

# 16. MVP Release Statement

At the end of 30 days, DevHive v0.1 should demonstrate one complete closed loop: a role-controlled developer works on an authorized branch, records TCC before pushing, the push is associated with an immutable engineering-memory record, and another authorized engineer can later retrieve the reasoning and history behind that change through RAG.